## Sheet1
PBIS | Note: The Ranking of the PBIs listed below are the highest prority are listed at the top and lowest at bottom. | TASKS | NOT STARTED | IN PROGRESS | COMPLETED
Name: | PBI9 |  | Coding
As: | Jody |  | Write Tests
I Want: | To be able to run a fair OPL election using a file containing ballot info. |  | Fill out Testing Templates
So that: | I can automatically run OPL elections since that’s a type of election my region uses. |  | Documentation
Acceptance Criteria: | OPL elections are able to be run without throwing errors and correctly distribute seats to the corresponding parties. |  | Run tests
Definition of Done: | Passes all system tests Passes all regression tests
Effort: | medium (3-4 hours)
PBI Author(s): | Sree Pemma, Samuel Wong
Name: | PBI1 |  | Coding
As: | An election official |  | Write Tests
I Want: | To be able to bring in multiple files at the same time |  | Fill out Testing Templates
So that: | I can run multiple elections with ballots from different locations |  | Documentation
Acceptance Criteria: | The user is able to input more than one election file for ballots when the program prompts them to and it executes each election file correctly with no errors thrown. |  | Run tests
Definition of Done: | Passes all regression tests Passes all system tests Documentation of tests using test logs is also done
Effort: | medium(4-5hrs)
PBI Author(s): | Sai Tallapragada
Name: | PBI4 |  | Coding
As: | An election official |  | Write Tests
I Want: | The system to only count IRV ballots with over half the candidates ranked towards the election and reject the ones that don’t have that. |  | Fill out Testing Templates
So that: | Ballots that have less than half (rounded up) of their candidates ranked won’t count towards the election as specified by state election officials. |  | Documentation
Acceptance Criteria: | The election can be run correctly by only counting the IRV ballots with at least half the candidates ranked and not counting the rest that don’t have half. |  | Run tests
Definition of Done: | Passes all unit tests Passes all system tests Passes all regression tests
Effort: | Medium (4-5 hours)
PBI Author(s): | Andy Chen
Name: | PBI8 |  | Coding
As: | An election official |  | Write Tests
I Want: | To be able to bring in PO election ballots via a csv format |  | Fill out Testing Templates
So that: | I am able to run a PO election with a csv file |  | Documentation
Acceptance Criteria: | The PO election is able to run successfully with the input of a csv file that contains the PO ballots to run the election and reads in ballot information correctly. |  | Run tests
Definition of Done: | Passes all unit tests Passes all regression tests Passes all system tests
Effort: | Small (3 hours)
PBI Author(s): | Sree Pemma